## Date_Calculator
Description	Lead Time (Days before start)	Deadlines	Complion Flag	Days Remaining	Task Start Date (1 week prior to due date)	Notes
	Today:	10/17/2023		Blank if complete	Course Code and Name:	TECH325 - Networking
Course Start Date		1/8/2024		83
SME Delivery Date	56	11/13/2023		27	11/6/2023
SME Midpoint Checkin	45	9/29/2023		-18	9/22/2023
SME Developer Contract Issued	90	8/15/2023	x			Due Oct 1, 2023 (put too early)
SME Identified	14	8/1/2023	x			Johnny Developer
Course Adjunct Contract Issued	21	12/18/2023		62	12/11/2023
Course Adjunct Identified	45	11/24/2023		38	11/17/2023	Jane Instructor